## Product Backlog
Product Name: | Exceptional Laptops and Supercomputers Always (ELSA) | [6 empty] | Complete Fields in Green!!!
Team ID: | Team Tic Tac
| Team Member Name | [5 empty] | Initials | Student ID
Required | David Trimino | [5 empty] | DT | 1001659459
Sprint # | Remaining | Completed This Sprint |  |  |  | Comment
0 | 16 |  |  |  | Total | Total number of features (in column H)
1 | 12 | 4 |  |  | 1 | Total features left at the end of Sprint #1
2 | 5 | 7 |  |  | 2 | Total features left at the end of Sprint #2
3 | 5 | 0 |  |  | 3 | ...and so on
4 | 5 | 0
5 | 5 | 0
Note: Priority and specs for unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
Sprints
Feature ID | Priority | Required | Bonus | Est | Planned | Status | As a... | I want to... | So that I can… | Notes
CUST | 1 | 1 |  | 3 | 1 | Finished in Sprint 1 | Sales Staff | Remember each customer’s name and contact info | Ship them products repeatedly
OPT | 2 | 1 |  | 8 | 1 | Finished in Sprint 1 | Inventory | Maintain a list of options for a desktop (e.g., disk, RAM, CPU) | Select them when designing a new desktop product
DESKT | 3 | 1 |  | 8 | 1 | Finished in Sprint 1 | Sales Staff | Define a new desktop configuration from options | Can quickly customize products for my customers
ORDER | 4 | 1 |  | 13 | 1 | Finished in Sprint 1 | Sales Staff | Associate a customer with one or more desktops into an order
WIN | 5 | 2 |  | 21 | 2 | Finished in Sprint 2 | Sales Staff | Replace the text interface with GUI main window | Use it more easily | Recommend baseling Nim from Lecture 13
OUTM | 6 | 2 |  | 5 | 2 | Finished in Sprint 2 | Sales Staff | Replace list of data records with main window list | Access the data directly in the window | Try using std::ostringstream to capture operator<< formating
INDIA | 7 | 2 |  | 8 | 2 | Finished in Sprint 2 | Sales Staff | Replace the data queries with series of dialog | Do everything within GUI | Use EntryDialog from Lecture 14
ABOUT | 8 | 2 |  | 1 | 2 | Finished in Sprint 2 | Director | Provide About dialog for doc licensesing | Avoid lawsuit
SAVE | 9 | 3 |  | 13 | 2 |  | Manager | Save the data to a default file (File > Save) | Persist our data through the years | This requires modifying the “model” to save and reload each object from a provided stream
SAVAS | 10 | 3 |  | 5 |  |  | Manager | Save the data to a default file (File > Save As ) | Persist our data through the years | Use Gtk::FileChooser
LOAD | 11 | 3 |  | 8 |  |  | Manager | Save the data to a default file (File > Open) | Persist our data through the years | Use Gtk::FileChooser
QRAM | 12 | 4 |  | 21 |  |  | Customer | Store and display additional RAM data | Ensure I purchase the correct product
DCUST | 13 | 4 |  | 8 |  |  | Sales Staff | Replace insert customer dialog with single dialog | Enter data more quickly
DOPT | 17 |  | 40 | 21 | 2 | Finished in Sprint 2 | Sales Staff | Repalce insert option dialog with single dialog | Enter data more quickly
DORD | 16 |  | 15 | 8 | 2 | Finished in Sprint 2 | Sales Staff | Replace insert order with single dialog | Enter data more quickly
DDESK | 18 |  | 25 | 13 | 2 | Finished in Sprint 2 | Sales Staff

## Sprint 01 Backlog
Sprint # | 1 |  | Complete Fields in Green!!!
Start on | 2020-03-03 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2020-03-24
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 16
Day 1 Left | 13 | 3
Day 2 Left | 13 | 0
Day 3 Left | 7 | 6
Day 4 Left | 3 | 4
Day 5 Left | 3 | 0
Day 6 Left | 0 | 3
Day 7 Left | 0 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | CUST |  | Write the Customer class | Completed Day 1 | Wrote the customer class
2 | CUST |  | Write operator<< for Customer | Completed Day 1 | Implemented the customer class
3 | CUST |  | Write Store::add_customer, num_customers, and customer | Completed Day 1 | TESTED AND PASSED
4 | OPT |  | Write the Options class sans to_string | Completed Day 3 | Did not test yet
5 | OPT |  | Write Options::to_string and its operator<< | Completed Day 3 | Did not test yet
6 | OPT |  | Write Store::add_option (to Store), num_options, and option | Completed Day 3 | TESTED AND PASSED
7 | DESKT |  | Write the Desktop class with add_option method | Completed Day 3 | Did not test yet
8 | DESKT |  | Write the Desktop::price method | Completed Day 3 | Did not test yet
9 | DESKT |  | Write operator<< for Desktop | Completed Day 3 | Did not test yet
10 | DESKT |  | Write Store::new_desktop, add_option (to desktop), num_desktops, and desktop | Completed Day 4 | Did not test yet
11 | ORDER |  | Write the Order associative class and constructor | Completed Day 4 | TESTED AND PASSED
12 | ORDER |  | Write Order::add_product | Completed Day 4 | Did not test yet
13 | ORDER |  | Write Order::price | Completed Day 4 | Did not test yet
14 | ORDER |  | Write Store::new_order, add_desktop, num_orders, and order | Completed Day 6 | Did not test yet
15 | ORDER |  | Integrate and test with cse1325_prof/elsa/sprint_1/main.cpp | Completed Day 6 | Did not test yet
16 | ORDER |  | Ensure ALL CODE is on GitHub by deadline! | Completed Day 6 | TESTED AND PASSED
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 02 Backlog
Sprint # | 2 |  | Complete Fields in Green!!!
Start on | 2020-03-24 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2020-03-31
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 13
Day 1 Left | 13 | 0
Day 2 Left | 13 | 0
Day 3 Left | 13 | 0
Day 4 Left | 12 | 1
Day 5 Left | 6 | 6
Day 6 Left | 0 | 6
Day 7 Left | 0 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | WIN |  | Update minwin.h | Completed Day 4 | Use baselining from Nim project (using mainwin.h from Nim)
2 | WIN |  | Clean code from mainwin.cpp and make sure it complies | Completed Day 5 | Remove any references to Nim and remove observer methods from above
3 | WIN |  | Add view, insert menu (insert new Customer, Options…) | Completed Day 5 | Don’t forget to activate signals to each (empty) observer
4 | OUTM |  | Implement get double,int string, and set/get msg methods | Completed Day 5
5 | INDIA |  | Implement inset/view customer methods | Completed Day 5 | Use baselining code from main in sprint 1 (for adding new customer)
6 | INDIA |  | Implement insert/view desktop methods | Completed Day 5 | Use baselining code from main in sprint1 (adding a new desktop)
7 | INDIA |  | Implement insert/view peripheral methods | Completed Day 5 | Use baselining code from main in sprint 1 (for adding new peripheral)
8 | INDIA |  | Implement insert/view order methods | Completed Day 6 | Use baselining code from main in sprint 1 (for adding new order)
9 | ABOUT |  | Create a company logo and give information to avoid lawsuit | Completed Day 6
10 | DCUST |  | Replace insert customer with a single dialog | Completed Day 6
11 | DDESK |  | Replace insert desktop with a single dialog | Completed Day 6
12 | DOPT |  | Replace insert option with a single dialog | Completed Day 6
13 | DORD |  | Replace insert order with a single dialog | Completed Day 6
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 03 Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2020-03-31 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2020-04-07
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 04 Backlog
Sprint # | 4 |  | Complete Fields in Green!!!
Start on | 2020-04-07 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2020-04-21
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 05 Backlog
Sprint # | 5 |  | Complete Fields in Green!!!
Start on | 2020-04-21 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2020-04-28
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84